## EHS Register_Mini CRA
StudyActionNo | StudyName_id | Guidewords | Deviation | Cause | Consequence | Safeguard | InitialRisk | Recommendations | ResidualRisk | DueDate | ProjectPhase_id | FutureAction | Organisation | Disipline | Subdisipline | Facility
RA-MONSOON-001 | RA - T and I activities during Monsoon | RA - T and I activities during Monsoon | Vessel Operations, unable to abort operation midway and Loss of control at any point during the entire sequence of operation- Heavy-Lifting, Rigging using S3000 Heavy Lift Crane, Davits | Vessel & Lifting operations during adverse weather conditions (monsoon period) - High sea states, high winds, heavy rain, etc. Unforecast adverse weather (Squall- sustained), wave > 2.5 meters and wind > 30 knots and high current | 1. Vessel contact / collision with BRG CPP / WHA when in drift on position, or other field marine vessels in vicinity causing hull and/or structural damage resulting in personnel injuries / fatalities, damage to vessel and project equipment, due to direct hazard exposures or hazard escalations (E.g. localized fire, man overboard, etc.). 2. Unsafe work conditions, unsafe acts leading to dropped / swing objects resulting in personnel injuries / fatalities, and vessel damage requiring repair and rectifications resulting in delays to complete work campaign. | - | 5C | To provide S3000 DP Capability Plot for work specific activity with environmental condition as force feed element. | 5B | 2021-10-06 | DDE |  | HESS | T&I | Marine | CPP
RA-MONSOON-002 | RA - T and I activities during Monsoon | Riser Stalk-on - Pipeline Lifting - Installation of CPP Riser (all sections) - Rigging operations (tugger wire etc.) (duration 5-8days) | Vessel Operations, unable to abort operation midway and Loss of control at any point during the entire sequence of operation- Heavy-Lifting, Rigging using S3000 Heavy Lift Crane, Davits | Vessel & Lifting operations during adverse weather conditions (monsoon period) - High sea states, high winds, heavy rain, etc. Unforecast adverse weather (Squall- sustained), wave > 2.5 meters and wind > 30 knots and high current | 1. Vessel contact / collision with BRG CPP / WHA when in drift on position, or other field marine vessels in vicinity causing hull and/or structural damage resulting in personnel injuries / fatalities, damage to vessel and project equipment, due to direct hazard exposures or hazard escalations (E.g. localized fire, man overboard, etc.). 2. Unsafe work conditions, unsafe acts leading to dropped / swing objects resulting in personnel injuries / fatalities, and vessel damage requiring repair and rectifications resulting in delays to complete work campaign. | - | 5C | Squall Monitoring - Position Tug on weather side to enable 3 hours squall alert that can be provided to Work Boat for swift mitigation actions. | 5B | 2021-10-06 | DDE |  | HESS | T&I | Marine | CPP
RA-MONSOON-003 | RA - T and I activities during Monsoon | Riser Stalk-on - Pipeline Lifting - Installation of CPP Riser (all sections) - Rigging operations (tugger wire etc.) (duration 5-8days) | Vessel Operations, unable to abort operation midway and Loss of control at any point during the entire sequence of operation- Heavy-Lifting, Rigging using S3000 Heavy Lift Crane, Davits | Vessel & Lifting operations during adverse weather conditions (monsoon period) - High sea states, high winds, heavy rain, etc. Unforecast adverse weather (Squall- sustained), wave > 2.5 meters and wind > 30 knots and high current | 1. Vessel contact / collision with BRG CPP / WHA when in drift on position, or other field marine vessels in vicinity causing hull and/or structural damage resulting in personnel injuries / fatalities, damage to vessel and project equipment, due to direct hazard exposures or hazard escalations (E.g. localized fire, man overboard, etc.). 2. Unsafe work conditions, unsafe acts leading to dropped / swing objects resulting in personnel injuries / fatalities, and vessel damage requiring repair and rectifications resulting in delays to complete work campaign. | - | 5C | ASOG to be reviewed and ensure that it is work specific and DP alerts correspond to environmental conditions. | 5B | 2021-10-06 | DDE |  | HESS | T&I | Marine | CPP
RA-MONSOON-004 | RA - T and I activities during Monsoon | Riser Stalk-on - Pipeline Lifting - Installation of CPP Riser (all sections) - Rigging operations (tugger wire etc.) (duration 5-8days) | Vessel Operations, unable to abort operation midway and Loss of control at any point during the entire sequence of operation- Heavy-Lifting, Rigging using S3000 Heavy Lift Crane, Davits | Vessel & Lifting operations during adverse weather conditions (monsoon period) - High sea states, high winds, heavy rain, etc. Unforecast adverse weather (Squall- sustained), wave > 2.5 meters and wind > 30 knots and high current | 1. Vessel contact / collision with BRG CPP / WHA when in drift on position, or other field marine vessels in vicinity causing hull and/or structural damage resulting in personnel injuries / fatalities, damage to vessel and project equipment, due to direct hazard exposures or hazard escalations (E.g. localized fire, man overboard, etc.). 2. Unsafe work conditions, unsafe acts leading to dropped / swing objects resulting in personnel injuries / fatalities, and vessel damage requiring repair and rectifications resulting in delays to complete work campaign. | - | 5C | Prepare a reasonable weather window prior to commencing work on each critical activity and possibility of aborting the activity. | 5B | 2021-10-06 | DDE |  | HESS | T&I | Pipeline | CPP
RA-MONSOON-005 | RA - T and I activities during Monsoon | Riser Stalk-on - Pipeline Lifting - Installation of CPP Riser (all sections) - Rigging operations (tugger wire etc.) (duration 5-8days) | Vessel Operations, unable to abort operation midway and Loss of control at any point during the entire sequence of operation- Heavy-Lifting, Rigging using S3000 Heavy Lift Crane, Davits | Vessel & Lifting operations during adverse weather conditions (monsoon period) - High sea states, high winds, heavy rain, etc. Unforecast adverse weather (Squall- sustained), wave > 2.5 meters and wind > 30 knots and high current | 1. Dropped object to sea requiring recovery of dropped riser section resulting in delays to complete work campaign 2. Dropped object to sea damaging pre-laid umbilical, requiring repair and rectifications resulting in delays to complete work campaign. 3.Potential extended shutdown as well as a weather window will need to coincide with shutdown periods | - | 5C | Consider possibility of aborting operations midway and detail out the steps for laying down pipeline + riser safely. | 5B | 2021-10-06 | DDE |  | HESS | T&I | Pipeline | CPP
RA-MONSOON-006 | RA - T and I activities during Monsoon | Lifting and Securing Riser Guard to CPP - Lift riser guard - Rigging Operations (tugger wire) - Secure/ tighten Riser Guard - De-rig lifting rigging from riser guard - Weld and NDT on top stopper plate and dog plate at clamp ring plate. (1-2days) | Vessel Operations - Heavy-Lifting, Rigging using S3000 Heavy Lift Crane, | Vessel & Lifting operations during adverse weather conditions (monsoon period) - High sea states, high winds, heavy rain, etc. Unforecast adverse weather (Squall- sustained), wave > 2.5 meters and wind > 30 knots and high current | Vessel contact / collision with BRG CPP / WHB when in drift on position, or other field marine vessels in vicinity causing hull and/or structural damage resulting in personnel injuries / fatalities, damage to vessel and project equipment, due to direct hazard exposures or hazard escalations (E.g. localized fire, man overboard, etc.). | 1. Vessel Squall Monitoring (using vessel radar) and Notices provided to vessel and vessel able to move away in time 2. Squall monitoring vessel to be placed on weather side of abut 2-3 nautical miles for monitoring 3. Utilization of wave rider buoy for live environmental indication. | 5B | To provide detail steps for aborting riser guard installation due to adverse weather. | 5B | 2021-10-06 | DDE |  | HESS | T&I | Pipeline | CPP
RA-MONSOON-007 | RA - T and I activities during Monsoon | 1. Riser Clamps Installation: - Flange Double Nut Installation - Tightening 2. Subsea Installation Aids derig/removal: - Knee Brace - 12” Pipeline Davit Lifting & Stopper Clamps - 12” Riser Stopper Clamps - 12” Riser Choker Slings (1-2 days) | Vessel Operations, Vessel Collision | Operations during monsoon period Adverse Weather conditions - Wave > 2.5 meters and wind > 30 knots and high current | Vessel contact / collision with BRG CPP / WHB when in drift on position, or other field marine vessels in vicinity causing hull and/or structural damage resulting in personnel injuries / fatalities, damage to vessel and project equipment, due to direct hazard exposures or hazard escalations (E.g. localized fire, man overboard, etc.). | 1. Weather Forecast and Monitoring - StormGeo forecast subscribed by Hess and provided to vessel, Akirakan forecast Subscribed by SFSB and provided to vessel 2. T&I Procedure - Limiting sea state criteria, vessel MOPO 2. Vessel Squall Monitoring (using vessel radar) 3. Squall alert and warning as part of subscription for weather forecast 4. T&I 500m Vessel Management Procedure (SFSB) - Requirement for working on Weather side risk assessment if approach is in drift on condition to platform, navigation envelope 5. Offshore T&I Project ERP (Hess / SFSB) - Contingency Procedures, Emergency communications and notifications 6. OVID, Marine Assurance, Crew Competency Assessment completed | 5B | To provide DPDSV DP Capability Plot for work specific activity with environmental condition as force feed element. | 5B | 2021-10-06 | DDE |  | HESS | T&I | Marine | CPP / WHB