## Action Items
id | StudyActionNo | StudyName | Facility | ProjectPhase | Cause | Safeguard | Consequence | Recommendations | InitialRisk | ResidualRisk | Response | Organisation | Disipline | Subdisipline | FutureAction | DueDate | QueSeries | QueSeriesTarget | Guidewords
5148 | Test-1 | HAZID | BRG WHB | 3 | 2. External Impact â€“ Dropped / Swung Object from platform activities (platform south hydrocarbon piping area is exposed to swing path) | 1. Integrity of crane & lifting apparatus. 2. Ex rated equipment (minimum Zone 2). 3. F&G detection & ESD systems 4. Emergency response equipment (i.e. muster area, liferaft, rescue equipment, rescue boat) 5. Fire extinguishers 6. Main Deck is plated and has no hydrocarbon process on this deck. 7. Pipeline is on Platform South while lifting from boat takes place from Platform North. | LOC of hydrocarbon condensate / gas leading to fire & explosion at BRG WHB & potential multiple fatalities | Place restriction on lifting over the pipeline on Platform South and the vent boom on Platform East. (No go zone will be indicated on Main Deck Layout Drawing.) | 5A |  |  | MMHE | EHS | Technical Safety |  | 2021-04-24 | 0 | 6
5149 | Test-2 | HAZID | BRG WHB | 3 | 5. Leaks from flange / connection during draining activities of portable drain tote tank. | 1. Flange management system 2. Ex rated equipment (minimum Zone 2). 3. F&G detection & ESD systems 4. Emergency response equipment (i.e. muster area, liferaft, rescue equipment, rescue boat) 5. Fire extinguishers 6. Draining takes place after topsides is depressurised. 7. Draining activity is manual. | LOC of hydrocarbon condensate / gas leading to potential injury to personnel | SOP to be developed for safe draining to tote tank. SOP to consider Hess Mercury Management Plan. | 3B |  |  | MMHE | HUC | HUC |  | 2021-04-24 | 0 | 0 | Condensate, NGL
5150 | Test-3 | HAZID | BRG WHB | 3 | 8. Loss of containment from riser flange | 1. Flange management system 2. Ex rated equipment (minimum Zone 2). 3. F&G detection & ESD systems 4. Emergency response equipment (i.e. muster area, liferaft, rescue equipment, rescue boat) 5. Fire extinguishers 6. Double block and bleed (DBB) provided for choke valve change out 7. JSA prior to maintenance activities. | LOC of hydrocarbon condensate / gas leading to fire & explosion at BRG WHB & potential multiple fatalities | Review requirement for firewall (instead of steel wall - radiation shield) to separate muster area from riser ESD valve in EERA. | 5A |  |  | MMHE | HUC | HUC |  | 2021-04-24 | 0 | 0 | Condensate, NGL
5151 | Test-4 | HAZID | BRG WHB | 3 | 8. Loss of containment from riser flange | 1. Flange management system 2. Ex rated equipment (minimum Zone 2). 3. F&G detection & ESD systems 4. Emergency response equipment (i.e. muster area, liferaft, rescue equipment, rescue boat) 5. Fire extinguishers 6. Double block and bleed (DBB) provided for choke valve change out 7. JSA prior to maintenance activities. | LOC of hydrocarbon condensate / gas leading to fire & explosion at BRG WHB & potential multiple fatalities | To consider extending the muster area to accommodate 25 pax at 0.8m2 per person, if possible. | 5A |  |  | MMHE | HUC | HUC |  | 2021-04-24 | 0 | 0 | Condensate, NGL
5152 | Test-5 | HAZID | BRG WHB | 3 | Lightning strike ignition of gas vent | 1. All venting is manual except blowdown during SIPROD. 2. Emergency response equipment (i.e. muster area, liferaft, rescue equipment, rescue boat) 3. Vent Dispersion and Ignited Vent Radiation Study will be used for sizing the vent boom. | Fire at gas vent | Vent Dispersion and Ignition Study to recommend reducing radiation on sensitive areas as low as possible considering structural constraints. | 2B |  |  | Hess | Safety | Safety |  | 2021-04-24 | 0 | 0 | Hydrocarbon gas
5153 | Test-6 | HAZID | BRG WHB | 3 | Lightning strike ignition of gas vent | 1. All venting is manual except blowdown during SIPROD. 2. Emergency response equipment (i.e. muster area, liferaft, rescue equipment, rescue boat) 3. Vent Dispersion and Ignited Vent Radiation Study will be used for sizing the vent boom. | Fire at gas vent | Review requirement for automatic blowdown during SIPROD (can this be manual from drilling rig). | 2B |  |  | Hess | EHS | Technical Safety |  | 2021-04-24 | 0 | 0 | Hydrocarbon gas
5154 | Test-7 | HAZID | BRG WHB | 3 | Leaks and hose break | 1. Methanol is only used for well start up and will be removed when not in use. 2. Coaming provided for the methanol tote tank. 3. ARAFFF provided in methanol tote tank area. 4. Ex rated equipment (minimum Zone 2). 5. Flame detector x 3 around the methanol skid 6. Emergency response equipment (i.e. muster area, liferaft, rescue equipment, rescue boat) | Methanol fire with potential injury to personnel. | Review whether permanent or temporary flame detector is require given that methanol is only used during well start up when the platform is manned. | 4B |  |  | MMHE | HUC | HUC |  | 2021-04-24 | 0 | 0 | Methanol
5155 | Test-8 | HAZID | BRG WHB | 3 | Leaks and hose break | 1. Methanol is only used for well start up and will be removed when not in use. 2. Coaming provided for the methanol tote tank. 3. ARAFFF provided in methanol tote tank area. 4. Ex rated equipment (minimum Zone 2). 5. Flame detector x 3 around the methanol skid 6. Emergency response equipment (i.e. muster area, liferaft, rescue equipment, rescue boat) | Methanol fire with potential injury to personnel. | Carry forward lesson learnt from previous hand injury accident in Hess to design the methanol tote tank flexible hose coupling. | 4B |  |  | MMHE | HUC | HUC |  | 2021-04-24 | 0 | 0 | Methanol
5156 | Test-9 | HAZID | BRG WHB | 3 | Relocation of crane boom rest | 1. PPE 2. PTW | Inaccessibility and potential for personnel to fall from height when unfastening crane boom rest for relocation. | Ensure sufficient access around crane boom rest on platform north west to allow for unbolting of boom rest safely. | 4A |  |  | MMHE | HUC | HUC |  | 2021-04-24 | 0 | 0
5157 | Test-10 | HAZID | BRG WHB | 3 | 1. Bad weather. 2. Crane Failure. 3. Operator error. | 1. Limitation on crane operation during bad weather. 2. Crane overload protection system. 3. Crane Operator competency. 4. Lifting equipment inspection and maintenance See 01.05 | LOC of hydrocarbon condensate / gas leading to fire & explosion at BRG WHB & potential multiple fatalities | Develop specific SOP for crane operations for crane package (SOP to include operating limit, robway switch, no go zones and etc.) | 5A |  |  | MMHE | HUC | HUC |  | 2021-04-24 | 0 | 6 | Overhead equipment
5158 | Test-11 | HAZID | BRG WHB | 3 | Crane boom length insufficient | 1. Material Handling Study | Inability to reach supply vessel laydown area | Outboard lifting PDMS review to be performed to ensure that the supply vessel laydown area can be reached. Material handling study to take account specific vessel proposed for this facility. | 3B |  |  | MMHE | HUC | HUC |  | 2021-04-24 | 0 | 0 | Overhead equipment
5159 | Test-12 | HAZID | BRG WHB | 3 | Swell greater than 2m wind greather than 20knots | 1. Weather forecast. | Boat can not approach the platform for personal transfer resulting in personal stranded on platform. | To review provision for personnel stranded on WHP. | 2C |  |  | MMHE | HUC | HUC |  | 2021-04-24 | 0 | 6 | Sea state
5160 | Test-13 | HAZID | BRG WHB | 3 | Low temperature during well start up due to pressure drop | 1. Methanol injection 2. Cage provided around cold surfaces in areas that can be reached by personnel | 1. Cold surfaces with potential for personnel injury | Review the personnel protection requirement for cold surfaces and warm up line during well start up | 4A |  |  | MMHE | HUC | HUC |  | 2021-04-24 | 0 | 0 | Process piping between â€“ 25 Â°C and â€“ 80 Â°C
5161 | Test-14 | HAZID | BRG WHB | 3 | 1. Damaged insulation 2. Unauthorized entry into transformer area | 1. Eletrical protection available given short circuit. 2. Earth fault protection 3. PTW to access transformer area 4. First aid and medical provision. | Potential fatality by electrocution. | Provide safety signage at transformer area. | 4B |  |  | MMHE | HUC | HUC |  | 2021-04-24 | 0 | 0 | Voltage > 50 V to 440 V in cables
5162 | Test-15 | HAZID | BRG WHB | 3 | Operating launcher door with nitrogen being present. | 1. Pigging procedure and pig door interlock. | Potential fatality due to asphyxiation. | Review working space allowance behind pig launcher to ensure is sufficient for intelligent pigging operation. | 4B |  |  | Hess | Marine | Marine |  | 2021-04-24 | 0 | 0 | Excessive N2
5163 | Test-16 | HAZID | BRG WHB | 3 | 1. Leak | 1. Piping design integrity and CRA cladding. 2. F&G detection & ESD systems 3. Emergency response equipment (i.e. muster area, liferaft) 4. EBA provided on CPP. | For hydrocarbon releases, see 01.05. CO2 / H2S release â€“ potential fatality due to asphyxiation toxic exposure. | Safety study will review a CPP dispersion analysis. | 4B |  |  | Hess | Marine | Marine |  | 2021-04-24 | 0 | 0 | Excessive CO2
5164 | Test-17 | HAZID | BRG WHB | 3 | 1. Well intervention activity | 1. Design integrity of wellhead. 2. Well integrity assurance program. 3. Well control and alarm. 4. Well shutdown mechanism. 5. Ex rated equipment (minimum Zone 2). However, there are some zone 1 area in wellbay 6. F&G detection & ESD systems hook up to the drilling rig (4 ESD pushbuttons on drilling rig) 7. Emergency response equipment (i.e. primary muster area at drilling rig, secondary muster area at Sump Deck,liferaft, rescue equipment, rescue boat) 8. Mud used to pressurised well during drilling. 9. Firewater monitor during drilling from Driling Rig. 10. Function and pressure test on BOP at fix schedule. 11. Maintain and verify dual barriers policy 12. SIMOPS procedure 13. SIPROD procedure by Rig | Well blowout leading to fire & explosion at BRG WHB & potential multiple fatalities | Locate pushbutton on rig in location such that inadvertent activation is avoided | 5A |  |  | MMHE | HUC | HUC |  | 2021-04-24 | 0 | 0 | Hydrocarbons in formation
5165 | Test-18 | HAZID | BRG WHB | 3 | Rigless well clean up during SIPROD | 1. Deluge system with redundant firewater pumps will be used to provide the water curtain around burner boom 2. Monitoring of radiation level during well clean up 3. Drilling risk assessment 4. Well clean up activity will be stopped if wind direction is from burner boom towards platform. | 1. High radiation from burner boom resulting injury to personal | Drilling contractor to share the radiation report and drilling risk assessment | 3C |  |  | MMHE | HUC | HUC |  | 2021-04-24 | 0 | 0 | High radiation from burner boom on the platform
5166 | Test-19 | HAZID | BRG WHB | 3 | Rigless well clean up during SIPROD | 1. Deluge system with redundant firewater pumps will be used to provide the water curtain around burner boom 2. Monitoring of radiation level during well clean up 3. Drilling risk assessment 4. Well clean up activity will be stopped if wind direction is from burner boom towards platform. | 1. High radiation from burner boom resulting injury to personal | Consider relocation burner boom or drilling to provide additional safety equipment and location. (Current fixed safety equipment location is just below the burner boom) | 3C |  |  | MMHE | HUC | HUC |  | 2021-04-24 | 0 | 0 | High radiation from burner boom on the platform
5167 | Test-20 | HAZID | BRG WHB | 3 | Rigless well clean up during SIPROD | 1. Noise study will be perform before SIPROD 2. Regular noise monitoring during well clean up 3. Hearing protection 4. Drilling risk assessment 5. Well clean up activity will be stopped if wind direction is from burner boom towards platform. | 2. High noise during well clean up resulting injury to personal | Drilling contractor to share the noise report and drilling risk assessment | 2C |  |  | MMHE | HUC | HUC |  | 2021-04-24 | 0 | 0 | High radiation from burner boom on the platform
5168 | Test-21 | HAZID | BRG WHB | 3 | Rigless well clean up during SIPROD | 1. Well clean up activity will be stopped if wind direction is from burner boom towards platform. 2. Deluge system with redundant firewater pumps will be used to provide the water curtain around burner boom | 3. Mercury vapour dispersion on platform resulting injury to personal | Dispersion and radiation report (for burner boom) to consider mercury. | 2C |  |  | Hess | Operations | Operations |  | 2021-04-24 | 0 | 0 | High radiation from burner boom on the platform
5169 | Test-22 | HAZID | BRG WHB | 3 | Rigless well clean up during SIPROD | 1. Well clean up activity will be stopped if wind direction is from burner boom towards platform. 2. Deluge system with redundant firewater pumps will be used to provide the water curtain around burner boom | 3. Mercury vapour dispersion on platform resulting injury to personal | Check burner boom location wrt prevailing wind at schedule time for rigless well clean up. | 2C |  |  | Hess | Operations | Operations |  | 2021-04-24 | 0 | 0 | High radiation from burner boom on the platform
5170 | Test-23 | HAZID | BRG WHB | 3 | Additional lighting requirement during well intervention | 1. Platform lighting already provided | Insufficient lighting for safe work leading to personal injury. | Well intervention to advise power requirement for lighting during well intervention and project to confirm whether sufficient power is available on platform. | 2B |  |  | Hess | Operations | Operations |  | 2021-04-24 | 0 | 0 | Lighting